## Read me
Topic | Meaning
Revision | D01 R03M / IH02 / 5 October 2026
Status | Review only. Not order, fabrication or energization authorization.
Prices | Blank means UNKNOWN; no prices have been invented.
Evidence | CAD/digital checks are not physical results.
Team | College/NGO funding; no college lab assumed; qualified physical services still needed.

## Milestones
Milestone | Current state | Evidence needed | Timing
Engineering review | Open | Named mechanical/electrical decisions and linked evidence | Dependent on reviewers and OEM inputs
Construction release | Not released | Frozen components, drawings and electrical schedule | After review
First safe run | Not done | Signed inspection/commissioning and measured airflow/pressure | After delivery, fabrication and assembly
Indoor performance | Not done | Controlled repeated trials and raw logs | After safe run
Outdoor pilot | Separate future scope | Site permission, weather/public-safety design and wind-dependent tests | Not scheduled

## Claims
Claim | Evidence status | Permitted wording
Physical prototype | 0 built | We have prepared the digital design for review.
Flow and cleaning | Unmeasured | The calculations are conditional; tests are planned.
Outdoor bubble | Unproven | The chain of zones is a research concept.
Costs and stock | Unquoted | Funding will be based on verified quotes.
Final name | Not selected | AQI Tower is the working name.

## Room scenarios
ASSUMED area m2 | ASSUMED height m | ASSUMED CADR m3/h | Target fraction reduced | Volume m3 | Ideal target minutes | Required CADR for30 min | Status
10 | 2.8 | 150 | 90% |  |  |  | Illustrative only; no measured D01 CADR
25 | 2.8 | 150 | 90% |  |  |  | Illustrative only; no measured D01 CADR
50 | 2.8 | 150 | 90% |  |  |  | Illustrative only; no measured D01 CADR
100 | 2.8 | 150 | 90% |  |  |  | Illustrative only; no measured D01 CADR

## Funding quotes
ID | Item | Quantity_basis | Vendor_or_service | Quote_date | Unit_cost_INR | Tax_INR | Delivery_INR | Lead_time | Scope_and_exclusions | Release_ID | Approval | Quoted_line_total_INR
F1-F4 | ARCTIC P14 Max ACFAN00287A | 4 | [8 empty] | UNQUOTED / NOT ORDER AUTHORIZATION
FL1-FL2 | IKEA STARKVIND104.633.30 particle filter | 2 | [8 empty] | UNQUOTED / NOT ORDER AUTHORIZATION
PS1 | Noctua NV-PS1 with NA-AC10 | 1 | [8 empty] | UNQUOTED / NOT ORDER AUTHORIZATION
SC1 | Noctua NA-FC1 | 1 | [8 empty] | UNQUOTED / NOT ORDER AUTHORIZATION
H1 | Noctua NA-FH1 with NA-EC1 | 1 | [8 empty] | UNQUOTED / NOT ORDER AUTHORIZATION
EXT | NA-EC1 300mm from NA-SEC1 kit | 2 candidate leads | [8 empty] | UNQUOTED / NOT ORDER AUTHORIZATION
CAB | R03M panels and cleats | 1 assembly | [8 empty] | UNQUOTED / NOT ORDER AUTHORIZATION
GUARD | R03M welded perforated guards | 2 assemblies | [8 empty] | UNQUOTED / NOT ORDER AUTHORIZATION
FIX | R03M fasteners and compression limiters | 1 scheduled set | [8 empty] | UNQUOTED / NOT ORDER AUTHORIZATION
SEAL | Filter/fan/penetration seals | 1 design set | [8 empty] | UNQUOTED / NOT ORDER AUTHORIZATION
FEET | Retained feet | 4 | [8 empty] | UNQUOTED / NOT ORDER AUTHORIZATION
PR1 | Protection and service isolation | 1 assembly | [8 empty] | UNQUOTED / NOT ORDER AUTHORIZATION
BOX | Controls enclosure and cable restraints | 1 assembly | [8 empty] | UNQUOTED / NOT ORDER AUTHORIZATION
TEST | Calibrated airflow/pressure/power/noise/PM measurement | 1 service scope | [8 empty] | UNQUOTED / NOT ORDER AUTHORIZATION
BUILD | Fabrication assembly and qualified review | 1 service scope | [8 empty] | UNQUOTED / NOT ORDER AUTHORIZATION