## Read me
Topic | Meaning
Revision | D01 R03M / IH02 / 5 October 2026
Status | Review only. Not order, fabrication or energization authorization.
Prices | Blank means UNKNOWN; no prices have been invented.
Evidence | CAD/digital checks are not physical results.
Team | College/NGO funding; no college lab assumed; qualified physical services still needed.

## Milestones
Milestone | Current state | Evidence needed | Timing
Engineering review | Open | Named mechanical/electrical decisions and linked evidence | Dependent on reviewers and OEM inputs
Construction release | Not released | Frozen components, drawings and electrical schedule | After review
First safe run | Not done | Signed inspection/commissioning and measured airflow/pressure | After delivery, fabrication and assembly
Indoor performance | Not done | Controlled repeated trials and raw logs | After safe run
Outdoor pilot | Separate future scope | Site permission, weather/public-safety design and wind-dependent tests | Not scheduled

## Claims
Claim | Evidence status | Permitted wording
Physical prototype | 0 built | We have prepared the digital design for review.
Flow and cleaning | Unmeasured | The calculations are conditional; tests are planned.
Outdoor bubble | Unproven | The chain of zones is a research concept.
Costs and stock | Unquoted | Funding will be based on verified quotes.
Final name | Not selected | AQI Tower is the working name.

## Room scenarios
ASSUMED area m2 | ASSUMED height m | ASSUMED CADR m3/h | Target fraction reduced | Volume m3 | Ideal target minutes | Required CADR for30 min | Status
10 | 2.8 | 150 | 90% |  |  |  | Illustrative only; no measured D01 CADR
25 | 2.8 | 150 | 90% |  |  |  | Illustrative only; no measured D01 CADR
50 | 2.8 | 150 | 90% |  |  |  | Illustrative only; no measured D01 CADR
100 | 2.8 | 150 | 90% |  |  |  | Illustrative only; no measured D01 CADR

## Funding quotes
ID | Item | Quantity_basis | Vendor_or_service | Quote_date | Unit_cost_INR | Tax_INR | Delivery_INR | Lead_time | Scope_and_exclusions | Release_ID | Approval | Quoted_line_total_INR
F1-F4 | ARCTIC P14 Max ACFAN00287A | 4 | [8 empty] | UNQUOTED / NOT ORDER AUTHORIZATION
FL1-FL2 | IKEA STARKVIND104.633.30 particle filter | 2 | [8 empty] | UNQUOTED / NOT ORDER AUTHORIZATION
PS1 | Noctua NV-PS1 with NA-AC10 | 1 | [8 empty] | UNQUOTED / NOT ORDER AUTHORIZATION
SC1 | Noctua NA-FC1 | 1 | [8 empty] | UNQUOTED / NOT ORDER AUTHORIZATION
H1 | Noctua NA-FH1 with NA-EC1 | 1 | [8 empty] | UNQUOTED / NOT ORDER AUTHORIZATION
EXT | NA-EC1 300mm from NA-SEC1 kit | 2 candidate leads | [8 empty] | UNQUOTED / NOT ORDER AUTHORIZATION
CAB | R03M panels and cleats | 1 assembly | [8 empty] | UNQUOTED / NOT ORDER AUTHORIZATION
GUARD | R03M welded perforated guards | 2 assemblies | [8 empty] | UNQUOTED / NOT ORDER AUTHORIZATION
FIX | R03M fasteners and compression limiters | 1 scheduled set | [8 empty] | UNQUOTED / NOT ORDER AUTHORIZATION
SEAL | Filter/fan/penetration seals | 1 design set | [8 empty] | UNQUOTED / NOT ORDER AUTHORIZATION
FEET | Retained feet | 4 | [8 empty] | UNQUOTED / NOT ORDER AUTHORIZATION
PR1 | Protection and service isolation | 1 assembly | [8 empty] | UNQUOTED / NOT ORDER AUTHORIZATION
BOX | Controls enclosure and cable restraints | 1 assembly | [8 empty] | UNQUOTED / NOT ORDER AUTHORIZATION
TEST | Calibrated airflow/pressure/power/noise/PM measurement | 1 service scope | [8 empty] | UNQUOTED / NOT ORDER AUTHORIZATION
BUILD | Fabrication assembly and qualified review | 1 service scope | [8 empty] | UNQUOTED / NOT ORDER AUTHORIZATION

## Release decisions
ID | Responsible_role_not_assigned_person | State | Decision | Required_work | Closure_evidence | Reviewer_name | Date | Disposition | Evidence_file
M01 | Mechanical | OPEN INTERNAL | Guard strength and reach | Select material and justified load/probe criteria; assess perforations, welds, side seams and attachments; verify unpowered sample. | Annotated calculation/drawing plus signed inspection result |  |  | OPEN
M02 | Mechanical | OPEN INTERNAL | Cabinet joints and stability | Check plywood/cleat grade, bolt bearing, edge distances, wood screw withdrawal, feet, whole mass/CG and cable pull; no lifting by lid. | Approved structural details and stability test record |  |  | OPEN
M03 | Mechanical | MIXED INPUT | Filter seal and service | Confirm exact filter frame/tolerance, gasket force/compression, flatness and feedthrough seals; verify safe supported removal. | Revised stops/retainers and fit/leak evidence |  |  | OPEN
M04 | Mechanical and electrical | WAITING OEM | Fan harness and protected entry | ARCTIC and Noctua connector/cable dimensions pending; Noctua220175. Complete insert, clamp, bend and retention design when received. | OEM evidence and updated integrated CAD/drawing |  |  | OPEN
E01 | Electrical and mechanical | OPEN INTERNAL | Hazard and protective function | Determine applicable requirements; reconcile fixed guards, isolated servicing and present restart requirements before choosing circuitry. | Signed functional allocation and explicit requirement disposition |  |  | OPEN
E02 | Electrical | OPEN INTERNAL | Rated circuit and enclosure | Select DC switching/protection/isolation, wire ratings, verified connectors and enclosure; check startup and auxiliary loads. No terminal guesses. | Circuit, cable schedule, ratings and physical layout |  |  | OPEN
E03 | Electrical | SITE AND PHYSICAL | Commissioning | Verify site supply and OEM adapter suitability; test isolation, stop/restart, supply recovery, abnormal/thermal behaviour under approved procedures. | Signed commissioning record before performance tests |  |  | OPEN
P01 | Mechanical and test lead | PHYSICAL DATA | Filter duty | Obtain exact clean/loaded curve or safe measured pressure/flow points; include all installed losses. | Accepted operating point with margin and replacement rule |  |  | OPEN
T01 | Test lead and project lead | TEAM DECISION | Acceptance targets and room | Agree indoor premises, measured flow/noise targets, room volume, instrument methods and PM test plan before trials. | Approved test plan and thresholds |  |  | OPEN
T02 | Test lead | AFTER RELEASE | Measured prototype results | Measure airflow, filter losses, bypass, noise, power and room PM with background/control observations. | Raw logs, calibration references and reviewed results |  |  | OPEN
C01 | Project lead and engineers | AFTER REVIEW | Procurement and change control | Confirm exact SKUs, quantities, real quotes, lead times and service scopes; authorize only released lines. | Approved BOM and revision-specific purchase/build authorization |  |  | OPEN
O01 | Separate future project | OUT OF INDOOR SCOPE | Public outdoor tower | Heat/rain/corrosion/tampering/anchoring and wind-dependent benefit require separate design and field validation. | Separate outdoor release; no bubble radius claimed |  |  | OPEN

## Parts register
ID | Quantity_basis | Item | Evidence_status | Unresolved | Source
F1-F4 | 4 | ARCTIC P14 Max ACFAN00287A | Exact OEM reference | Delivered revision and cable details; guard and duty integration | Electrical BOM; OEM sources S1
FL1-FL2 | 2 | IKEA STARKVIND104.633.30 particle filter | Experimental reference only | 370x290x40 catalogue envelope; pressure curve/frame/seal tolerances unknown; OEM specifies STARKVIND use only | r02_adapter/README.md
PS1 | 1 | Noctua NV-PS1 with NA-AC10 | Exact OEM reference | 12V2A24W; startup/auxiliary/site suitability not closed | Electrical BOM S2/S6
SC1 | 1 | Noctua NA-FC1 | Exact OEM reference | Speed controller is not protective isolation | Electrical BOM S3
H1 | 1 | Noctua NA-FH1 with NA-EC1 | Exact OEM reference | 24W selected input; self-reset; only port1 RPM upstream; SATA unused | Electrical BOM S4/S5
EXT | 2 candidate leads | NA-EC1 300mm from NA-SEC1 kit | Candidate not selected | Kit contains3 leads; dimensions pending; check total connection count before purchase | Harness README
CAB | 1 assembly | R03M panels and cleats | Custom proposed geometry | Grade/joints/strength/finish unreleased; panel inventory is controlling geometry | CAD_PART_INVENTORY.csv and15 DXFs
GUARD | 2 assemblies | R03M welded perforated guards | Custom proposed geometry | Strength/reach/weld criteria unreleased;1mm not approved | GUARD_BLANKS.csv; guard_pattern.json
FIX | 1 scheduled set | R03M fasteners and compression limiters | Proposed geometry | Use FASTENER_SCHEDULE; do not add inventory quantities again; grade/torque unresolved | FASTENER_SCHEDULE.csv
SEAL | 1 design set | Filter/fan/penetration seals | Unselected material | Gasket dimensions are installed envelopes, not a compression specification | CAD inventory; mechanical_screen.json
FEET | 4 | Retained feet | Proposed geometry | Material/bearing/stability not released | Mechanical package
PR1 | 1 assembly | Protection and service isolation | UNSELECTED | Not replaced by hub fuse, PWM or software model | Electrical interfaces J09/J11
BOX | 1 assembly | Controls enclosure and cable restraints | UNSELECTED | 140x100x40 reservation is not selected enclosure or complete fit | Electrical package
TEST | 1 service scope | Calibrated airflow/pressure/power/noise/PM measurement | UNSELECTED | Rent or commission test service; no college lab assumed | Validation package
BUILD | 1 service scope | Fabrication assembly and qualified review | UNSELECTED | Internal engineers review; outsource workshop work as needed | Review register

## Pressure screening
total_m3h | per_filter_m3h | reducer_K | fan_Pa | plenum_Pa | inner_guard_Pa | outer_guard_Pa | installation_Pa | reducer_Pa | nonfilter_Pa | filter_allowance_Pa
200 | 100 | 0.5 | 32.6 | 0.86774 | 2.2088 | 2.2088 | 0.57849 | 0.025921 | 5.8898 | 26.7102
200 | 100 | 1 | 32.6 | 0.86774 | 2.2088 | 2.2088 | 0.57849 | 0.051842 | 5.9157 | 26.6842
200 | 100 | 2 | 32.6 | 0.86774 | 2.2088 | 2.2088 | 0.57849 | 0.10368 | 5.9676 | 26.6324
250 | 125 | 0.5 | 30.0939 | 1.3558 | 3.4513 | 3.4513 | 0.90389 | 0.040502 | 9.2028 | 20.8911
250 | 125 | 1 | 30.0939 | 1.3558 | 3.4513 | 3.4513 | 0.90389 | 0.081003 | 9.2433 | 20.8506
250 | 125 | 2 | 30.0939 | 1.3558 | 3.4513 | 3.4513 | 0.90389 | 0.16201 | 9.3244 | 20.7696
300 | 150 | 0.5 | 27.6265 | 1.9524 | 4.9699 | 4.9699 | 1.3016 | 0.058322 | 13.2521 | 14.3744
300 | 150 | 1 | 27.6265 | 1.9524 | 4.9699 | 4.9699 | 1.3016 | 0.11664 | 13.3104 | 14.3161
300 | 150 | 2 | 27.6265 | 1.9524 | 4.9699 | 4.9699 | 1.3016 | 0.23329 | 13.4271 | 14.1994
350 | 175 | 0.5 | 25.2677 | 2.6574 | 6.7646 | 6.7646 | 1.7716 | 0.079383 | 18.0376 | 7.2301
350 | 175 | 1 | 25.2677 | 2.6574 | 6.7646 | 6.7646 | 1.7716 | 0.15877 | 18.117 | 7.1508
350 | 175 | 2 | 25.2677 | 2.6574 | 6.7646 | 6.7646 | 1.7716 | 0.31753 | 18.2757 | 6.992
400 | 200 | 0.5 | 22.8339 | 3.4709 | 8.8353 | 8.8353 | 2.314 | 0.10368 | 23.5593 | -0.72543
400 | 200 | 1 | 22.8339 | 3.4709 | 8.8353 | 8.8353 | 2.314 | 0.20737 | 23.663 | -0.82912
400 | 200 | 2 | 22.8339 | 3.4709 | 8.8353 | 8.8353 | 2.314 | 0.41474 | 23.8703 | -1.0365

## Pressure assumptions
Field | Value
Status | CONDITIONAL SCREEN - NOT ACTUAL FLOW
Assumptions | 2800 rpm OEM numeric curve; equal sharing among four fans and two parallel filters; density1.2; guard K1.5 each; plenum K1.5 and installation K1 on fan-aperture velocity. Reducer K0.5/1/2. Loss coefficients unverified; reducer/plenum may overlap. Static/installed compatibility unresolved. No loaded filter curve.
Filter data | No measured clean or loaded curve; allowance is not actual loss

## Fasteners
item | qty | spec | status
M5 reducer studs | 16 | 12 x60 mm;4 x40 mm;32 nuts8AFx5;32 washers15ODx1.2 (bore5.3 assumed) | PROPOSED; external thread projection2.8mm; inner3.8mm
Seal compression limiters | 24 | 16 outer OD10/ID5.5 x3;8 inner OD6.5/ID4.5 x36 | ASSUMED nominal gaps; force/tolerance/actual filter thickness unknown
Fan fastenings | 16 | M4x50 cap screw;32 washers12ODx1;16 nuts7AFx5 | PROPOSED;6mm nominal thread projection; fan corner bearing strength unknown
Cabinet through joints | 32 | M4x40 cap screws;64 washers12ODx1;32 nuts7AFx5 | PROPOSED;4mm nominal thread projection; wood bearing/edge and clamp load not approved
Top/base wood screws | 8 | 4 top4x20;4 base4x25;8 washers;head7dia x4 envelope | Core only; thread/pilot, wood grade and end-grain withdrawal must be verified; never lift by lid
Foot retention | 4 | M4x30 cap screw;8 washers12ODx1;4 nuts7AFx5;4 feet with12dia x9 recess | PROPOSED; head4mm above floor;3mm nominal thread projection; foot material strength unknown
Retained adapter M4 hardware | 8 | 8 M4x80 studs;4 M4x25 ledge screws;28 nuts;32 washers | R02H geometry retained; sealing washers separate
Independent guard bolts | 8 | 8 M4x20 screws;8 nuts;16 washers | R02G mounting stacks retained; welded cage replaces rivets

## Display dimensions
CAD object | Kind | X mm | Y mm | Z mm | Limit
M01_Base | panel | 550 | 360 | 9 | Mesh bounding box; no tolerance or manufacturing release
M02_Left | panel | 9 | 360 | 542 | Mesh bounding box; no tolerance or manufacturing release
M02_Right | panel | 9 | 360 | 542 | Mesh bounding box; no tolerance or manufacturing release
M03_Seat_Front | panel | 532 | 9 | 542 | Mesh bounding box; no tolerance or manufacturing release
S01_Filter_seal_Front | seal | 495.3 | 3 | 495.3 | Mesh bounding box; no tolerance or manufacturing release
M03_Seat_Rear | panel | 532 | 9 | 542 | Mesh bounding box; no tolerance or manufacturing release
S01_Filter_seal_Rear | seal | 495.3 | 3 | 495.3 | Mesh bounding box; no tolerance or manufacturing release
S02_Fan_seal_1 | seal | 140 | 140 | 1 | Mesh bounding box; no tolerance or manufacturing release
F02_P14_Max_1 | fan | 140 | 140 | 27 | Mesh bounding box; no tolerance or manufacturing release
S02_Fan_seal_2 | seal | 140 | 140 | 1 | Mesh bounding box; no tolerance or manufacturing release
F02_P14_Max_2 | fan | 140 | 140 | 27 | Mesh bounding box; no tolerance or manufacturing release
S02_Fan_seal_3 | seal | 140 | 140 | 1 | Mesh bounding box; no tolerance or manufacturing release
F02_P14_Max_3 | fan | 140 | 140 | 27 | Mesh bounding box; no tolerance or manufacturing release
S02_Fan_seal_4 | seal | 140 | 140 | 1 | Mesh bounding box; no tolerance or manufacturing release
F02_P14_Max_4 | fan | 140 | 140 | 27 | Mesh bounding box; no tolerance or manufacturing release
M06_Fan_plate | panel | 550 | 360 | 9 | Mesh bounding box; no tolerance or manufacturing release
M07_Cleat_9_9 | support | 20 | 20 | 542 | Mesh bounding box; no tolerance or manufacturing release
M07_Cleat_9_331 | support | 20 | 20 | 542 | Mesh bounding box; no tolerance or manufacturing release
M07_Cleat_521_9 | support | 20 | 20 | 542 | Mesh bounding box; no tolerance or manufacturing release
M07_Cleat_521_331 | support | 20 | 20 | 542 | Mesh bounding box; no tolerance or manufacturing release
M08_Foot_25_15 | support | 30 | 30 | 20 | Mesh bounding box; no tolerance or manufacturing release
M08_Foot_25_315 | support | 30 | 30 | 20 | Mesh bounding box; no tolerance or manufacturing release
M08_Foot_495_15 | support | 30 | 30 | 20 | Mesh bounding box; no tolerance or manufacturing release
M08_Foot_495_315 | support | 30 | 30 | 20 | Mesh bounding box; no tolerance or manufacturing release
E01_Control_box_RESERVATION | reservation | 40 | 140 | 100 | Mesh bounding box; no tolerance or manufacturing release
H10_False_19_19 | hardware | 2.398 | 2.399 | 25 | Mesh bounding box; no tolerance or manufacturing release
H10_False_19_341 | hardware | 2.398 | 2.399 | 25 | Mesh bounding box; no tolerance or manufacturing release
H10_False_531_19 | hardware | 2.398 | 2.399 | 25 | Mesh bounding box; no tolerance or manufacturing release
H10_False_531_341 | hardware | 2.398 | 2.399 | 25 | Mesh bounding box; no tolerance or manufacturing release
H10_True_19_19 | hardware | 2.398 | 2.399 | 20 | Mesh bounding box; no tolerance or manufacturing release
H10_True_19_341 | hardware | 2.398 | 2.399 | 20 | Mesh bounding box; no tolerance or manufacturing release
H10_True_531_19 | hardware | 2.398 | 2.399 | 20 | Mesh bounding box; no tolerance or manufacturing release
H10_True_531_341 | hardware | 2.398 | 2.399 | 20 | Mesh bounding box; no tolerance or manufacturing release
E02_Cable_corridor_0 | reservation | 130 | 11.996 | 12 | Mesh bounding box; no tolerance or manufacturing release
E02_Cable_corridor_1 | reservation | 12 | 11.996 | 105 | Mesh bounding box; no tolerance or manufacturing release
A01_Reducer_Front | panel | 550 | 9 | 550 | Mesh bounding box; no tolerance or manufacturing release
A02_Filter_gasket_Front | seal | 370 | 3 | 290 | Mesh bounding box; no tolerance or manufacturing release
A03_STARKVIND_envelope_Front | filter | 370 | 40 | 290 | Mesh bounding box; no tolerance or manufacturing release
A04_Retainer_Front | panel | 410 | 9 | 330 | Mesh bounding box; no tolerance or manufacturing release
A06_Feedthrough_seal_0_Front | seal | 9.997 | 1 | 10 | Mesh bounding box; no tolerance or manufacturing release
A06_Feedthrough_seal_1_Front | seal | 9.997 | 1 | 10 | Mesh bounding box; no tolerance or manufacturing release
A06_Feedthrough_seal_2_Front | seal | 9.997 | 1 | 10 | Mesh bounding box; no tolerance or manufacturing release
A06_Feedthrough_seal_3_Front | seal | 9.997 | 1 | 10 | Mesh bounding box; no tolerance or manufacturing release
A07_Ledge_130_Front | support | 30 | 43 | 22 | Mesh bounding box; no tolerance or manufacturing release
A09_Ledge_seal_130_Front | seal | 9.997 | 1 | 10 | Mesh bounding box; no tolerance or manufacturing release
A07_Ledge_390_Front | support | 30 | 43 | 22 | Mesh bounding box; no tolerance or manufacturing release
A09_Ledge_seal_390_Front | seal | 9.997 | 1 | 10 | Mesh bounding box; no tolerance or manufacturing release
A01_Reducer_Rear | panel | 550 | 9 | 550 | Mesh bounding box; no tolerance or manufacturing release
A02_Filter_gasket_Rear | seal | 370 | 3 | 290 | Mesh bounding box; no tolerance or manufacturing release
A03_STARKVIND_envelope_Rear | filter | 370 | 40 | 290 | Mesh bounding box; no tolerance or manufacturing release
A04_Retainer_Rear | panel | 410 | 9 | 330 | Mesh bounding box; no tolerance or manufacturing release
A06_Feedthrough_seal_0_Rear | seal | 9.997 | 1 | 10 | Mesh bounding box; no tolerance or manufacturing release
A06_Feedthrough_seal_1_Rear | seal | 9.997 | 1 | 10 | Mesh bounding box; no tolerance or manufacturing release
A06_Feedthrough_seal_2_Rear | seal | 9.997 | 1 | 10 | Mesh bounding box; no tolerance or manufacturing release
A06_Feedthrough_seal_3_Rear | seal | 9.997 | 1 | 10 | Mesh bounding box; no tolerance or manufacturing release
A07_Ledge_130_Rear | support | 30 | 43 | 22 | Mesh bounding box; no tolerance or manufacturing release
A09_Ledge_seal_130_Rear | seal | 9.997 | 1 | 10 | Mesh bounding box; no tolerance or manufacturing release
A07_Ledge_390_Rear | support | 30 | 43 | 22 | Mesh bounding box; no tolerance or manufacturing release
A09_Ledge_seal_390_Rear | seal | 9.997 | 1 | 10 | Mesh bounding box; no tolerance or manufacturing release
A05_Stud_0_Front | hardware | 4 | 80 | 4 | Mesh bounding box; no tolerance or manufacturing release
H10_Service_washer_0_Front | hardware | 11.996 | 1 | 12 | Mesh bounding box; no tolerance or manufacturing release
H10_Outer_fixed_washer_0_Front | hardware | 11.996 | 1 | 12 | Mesh bounding box; no tolerance or manufacturing release
H10_Inner_fixed_washer_0_Front | hardware | 11.996 | 1 | 12 | Mesh bounding box; no tolerance or manufacturing release
H11_Service_nut_0_Front | hardware | 8.083 | 5 | 7 | Mesh bounding box; no tolerance or manufacturing release
H11_Outer_fixed_nut_0_Front | hardware | 8.083 | 5 | 7 | Mesh bounding box; no tolerance or manufacturing release
H11_Inner_fixed_nut_0_Front | hardware | 8.083 | 5 | 7 | Mesh bounding box; no tolerance or manufacturing release
A05_Stud_1_Front | hardware | 4 | 80 | 4 | Mesh bounding box; no tolerance or manufacturing release
H10_Service_washer_1_Front | hardware | 11.996 | 1 | 12 | Mesh bounding box; no tolerance or manufacturing release
H10_Outer_fixed_washer_1_Front | hardware | 11.996 | 1 | 12 | Mesh bounding box; no tolerance or manufacturing release
H10_Inner_fixed_washer_1_Front | hardware | 11.996 | 1 | 12 | Mesh bounding box; no tolerance or manufacturing release
H11_Service_nut_1_Front | hardware | 8.083 | 5 | 7 | Mesh bounding box; no tolerance or manufacturing release
H11_Outer_fixed_nut_1_Front | hardware | 8.083 | 5 | 7 | Mesh bounding box; no tolerance or manufacturing release
H11_Inner_fixed_nut_1_Front | hardware | 8.083 | 5 | 7 | Mesh bounding box; no tolerance or manufacturing release
A05_Stud_2_Front | hardware | 4 | 80 | 4 | Mesh bounding box; no tolerance or manufacturing release
H10_Service_washer_2_Front | hardware | 11.996 | 1 | 12 | Mesh bounding box; no tolerance or manufacturing release
H10_Outer_fixed_washer_2_Front | hardware | 11.996 | 1 | 12 | Mesh bounding box; no tolerance or manufacturing release
H10_Inner_fixed_washer_2_Front | hardware | 11.996 | 1 | 12 | Mesh bounding box; no tolerance or manufacturing release
H11_Service_nut_2_Front | hardware | 8.083 | 5 | 7 | Mesh bounding box; no tolerance or manufacturing release
H11_Outer_fixed_nut_2_Front | hardware | 8.083 | 5 | 7 | Mesh bounding box; no tolerance or manufacturing release
H11_Inner_fixed_nut_2_Front | hardware | 8.083 | 5 | 7 | Mesh bounding box; no tolerance or manufacturing release
A05_Stud_3_Front | hardware | 4 | 80 | 4 | Mesh bounding box; no tolerance or manufacturing release
H10_Service_washer_3_Front | hardware | 11.996 | 1 | 12 | Mesh bounding box; no tolerance or manufacturing release
H10_Outer_fixed_washer_3_Front | hardware | 11.996 | 1 | 12 | Mesh bounding box; no tolerance or manufacturing release
H10_Inner_fixed_washer_3_Front | hardware | 11.996 | 1 | 12 | Mesh bounding box; no tolerance or manufacturing release
H11_Service_nut_3_Front | hardware | 8.083 | 5 | 7 | Mesh bounding box; no tolerance or manufacturing release
H11_Outer_fixed_nut_3_Front | hardware | 8.083 | 5 | 7 | Mesh bounding box; no tolerance or manufacturing release
H11_Inner_fixed_nut_3_Front | hardware | 8.083 | 5 | 7 | Mesh bounding box; no tolerance or manufacturing release
A08_Ledge_bolt_130_Front | hardware | 6.998 | 29 | 7 | Mesh bounding box; no tolerance or manufacturing release
H12_Outer_washer_130_Front | hardware | 11.996 | 1 | 12 | Mesh bounding box; no tolerance or manufacturing release
H12_Inner_washer_130_Front | hardware | 11.996 | 1 | 12 | Mesh bounding box; no tolerance or manufacturing release
H13_Ledge_nut_130_Front | hardware | 8.083 | 5 | 7 | Mesh bounding box; no tolerance or manufacturing release
A08_Ledge_bolt_390_Front | hardware | 6.998 | 29 | 7 | Mesh bounding box; no tolerance or manufacturing release
H12_Outer_washer_390_Front | hardware | 11.996 | 1 | 12 | Mesh bounding box; no tolerance or manufacturing release
H12_Inner_washer_390_Front | hardware | 11.996 | 1 | 12 | Mesh bounding box; no tolerance or manufacturing release
H13_Ledge_nut_390_Front | hardware | 8.083 | 5 | 7 | Mesh bounding box; no tolerance or manufacturing release
A05_Stud_0_Rear | hardware | 4 | 80 | 4 | Mesh bounding box; no tolerance or manufacturing release
H10_Service_washer_0_Rear | hardware | 11.996 | 1 | 12 | Mesh bounding box; no tolerance or manufacturing release
H10_Outer_fixed_washer_0_Rear | hardware | 11.996 | 1 | 12 | Mesh bounding box; no tolerance or manufacturing release
H10_Inner_fixed_washer_0_Rear | hardware | 11.996 | 1 | 12 | Mesh bounding box; no tolerance or manufacturing release
H11_Service_nut_0_Rear | hardware | 8.083 | 5 | 7 | Mesh bounding box; no tolerance or manufacturing release
H11_Outer_fixed_nut_0_Rear | hardware | 8.083 | 5 | 7 | Mesh bounding box; no tolerance or manufacturing release
H11_Inner_fixed_nut_0_Rear | hardware | 8.083 | 5 | 7 | Mesh bounding box; no tolerance or manufacturing release
A05_Stud_1_Rear | hardware | 4 | 80 | 4 | Mesh bounding box; no tolerance or manufacturing release
H10_Service_washer_1_Rear | hardware | 11.996 | 1 | 12 | Mesh bounding box; no tolerance or manufacturing release
H10_Outer_fixed_washer_1_Rear | hardware | 11.996 | 1 | 12 | Mesh bounding box; no tolerance or manufacturing release
H10_Inner_fixed_washer_1_Rear | hardware | 11.996 | 1 | 12 | Mesh bounding box; no tolerance or manufacturing release
H11_Service_nut_1_Rear | hardware | 8.083 | 5 | 7 | Mesh bounding box; no tolerance or manufacturing release
H11_Outer_fixed_nut_1_Rear | hardware | 8.083 | 5 | 7 | Mesh bounding box; no tolerance or manufacturing release
H11_Inner_fixed_nut_1_Rear | hardware | 8.083 | 5 | 7 | Mesh bounding box; no tolerance or manufacturing release
A05_Stud_2_Rear | hardware | 4 | 80 | 4 | Mesh bounding box; no tolerance or manufacturing release
H10_Service_washer_2_Rear | hardware | 11.996 | 1 | 12 | Mesh bounding box; no tolerance or manufacturing release
H10_Outer_fixed_washer_2_Rear | hardware | 11.996 | 1 | 12 | Mesh bounding box; no tolerance or manufacturing release
H10_Inner_fixed_washer_2_Rear | hardware | 11.996 | 1 | 12 | Mesh bounding box; no tolerance or manufacturing release
H11_Service_nut_2_Rear | hardware | 8.083 | 5 | 7 | Mesh bounding box; no tolerance or manufacturing release
H11_Outer_fixed_nut_2_Rear | hardware | 8.083 | 5 | 7 | Mesh bounding box; no tolerance or manufacturing release
H11_Inner_fixed_nut_2_Rear | hardware | 8.083 | 5 | 7 | Mesh bounding box; no tolerance or manufacturing release
A05_Stud_3_Rear | hardware | 4 | 80 | 4 | Mesh bounding box; no tolerance or manufacturing release
H10_Service_washer_3_Rear | hardware | 11.996 | 1 | 12 | Mesh bounding box; no tolerance or manufacturing release
H10_Outer_fixed_washer_3_Rear | hardware | 11.996 | 1 | 12 | Mesh bounding box; no tolerance or manufacturing release
H10_Inner_fixed_washer_3_Rear | hardware | 11.996 | 1 | 12 | Mesh bounding box; no tolerance or manufacturing release
H11_Service_nut_3_Rear | hardware | 8.083 | 5 | 7 | Mesh bounding box; no tolerance or manufacturing release
H11_Outer_fixed_nut_3_Rear | hardware | 8.083 | 5 | 7 | Mesh bounding box; no tolerance or manufacturing release
H11_Inner_fixed_nut_3_Rear | hardware | 8.083 | 5 | 7 | Mesh bounding box; no tolerance or manufacturing release
A08_Ledge_bolt_130_Rear | hardware | 6.998 | 29 | 7 | Mesh bounding box; no tolerance or manufacturing release
H12_Outer_washer_130_Rear | hardware | 11.996 | 1 | 12 | Mesh bounding box; no tolerance or manufacturing release
H12_Inner_washer_130_Rear | hardware | 11.996 | 1 | 12 | Mesh bounding box; no tolerance or manufacturing release
H13_Ledge_nut_130_Rear | hardware | 8.083 | 5 | 7 | Mesh bounding box; no tolerance or manufacturing release
A08_Ledge_bolt_390_Rear | hardware | 6.998 | 29 | 7 | Mesh bounding box; no tolerance or manufacturing release
H12_Outer_washer_390_Rear | hardware | 11.996 | 1 | 12 | Mesh bounding box; no tolerance or manufacturing release
H12_Inner_washer_390_Rear | hardware | 11.996 | 1 | 12 | Mesh bounding box; no tolerance or manufacturing release
H13_Ledge_nut_390_Rear | hardware | 8.083 | 5 | 7 | Mesh bounding box; no tolerance or manufacturing release
J01_Outer_105_120_Screw | hardware | 7 | 6.998 | 24 | Mesh bounding box; no tolerance or manufacturing release
J01_Outer_105_120_Upper_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
J01_Outer_105_120_Lower_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
J01_Outer_105_120_Nut | hardware | 8.083 | 7 | 5 | Mesh bounding box; no tolerance or manufacturing release
J01_Outer_105_240_Screw | hardware | 7 | 6.998 | 24 | Mesh bounding box; no tolerance or manufacturing release
J01_Outer_105_240_Upper_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
J01_Outer_105_240_Lower_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
J01_Outer_105_240_Nut | hardware | 8.083 | 7 | 5 | Mesh bounding box; no tolerance or manufacturing release
J01_Outer_445_120_Screw | hardware | 7 | 6.998 | 24 | Mesh bounding box; no tolerance or manufacturing release
J01_Outer_445_120_Upper_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
J01_Outer_445_120_Lower_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
J01_Outer_445_120_Nut | hardware | 8.083 | 7 | 5 | Mesh bounding box; no tolerance or manufacturing release
J01_Outer_445_240_Screw | hardware | 7 | 6.998 | 24 | Mesh bounding box; no tolerance or manufacturing release
J01_Outer_445_240_Upper_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
J01_Outer_445_240_Lower_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
J01_Outer_445_240_Nut | hardware | 8.083 | 7 | 5 | Mesh bounding box; no tolerance or manufacturing release
J01_Inner_105_60_Screw | hardware | 7 | 6.998 | 24 | Mesh bounding box; no tolerance or manufacturing release
J01_Inner_105_60_Upper_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
J01_Inner_105_60_Lower_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
J01_Inner_105_60_Nut | hardware | 8.083 | 7 | 5 | Mesh bounding box; no tolerance or manufacturing release
J01_Inner_105_300_Screw | hardware | 7 | 6.998 | 24 | Mesh bounding box; no tolerance or manufacturing release
J01_Inner_105_300_Upper_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
J01_Inner_105_300_Lower_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
J01_Inner_105_300_Nut | hardware | 8.083 | 7 | 5 | Mesh bounding box; no tolerance or manufacturing release
J01_Inner_445_60_Screw | hardware | 7 | 6.998 | 24 | Mesh bounding box; no tolerance or manufacturing release
J01_Inner_445_60_Upper_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
J01_Inner_445_60_Lower_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
J01_Inner_445_60_Nut | hardware | 8.083 | 7 | 5 | Mesh bounding box; no tolerance or manufacturing release
J01_Inner_445_300_Screw | hardware | 7 | 6.998 | 24 | Mesh bounding box; no tolerance or manufacturing release
J01_Inner_445_300_Upper_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
J01_Inner_445_300_Lower_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
J01_Inner_445_300_Nut | hardware | 8.083 | 7 | 5 | Mesh bounding box; no tolerance or manufacturing release
G10_Outer_fabricated_guard | guard | 360 | 320 | 51 | Mesh bounding box; no tolerance or manufacturing release
G10_Inner_fabricated_guard | guard | 360 | 320 | 41 | Mesh bounding box; no tolerance or manufacturing release
K01_Front_0_stud | hardware | 4.999 | 60 | 4.999 | Mesh bounding box; no tolerance or manufacturing release
K01_Front_0_outer_washer | hardware | 15 | 1.2 | 14.995 | Mesh bounding box; no tolerance or manufacturing release
K01_Front_0_inner_washer | hardware | 15 | 1.2 | 14.995 | Mesh bounding box; no tolerance or manufacturing release
K01_Front_0_outer_nut | hardware | 9.238 | 5 | 8 | Mesh bounding box; no tolerance or manufacturing release
K01_Front_0_inner_nut | hardware | 9.238 | 5 | 8 | Mesh bounding box; no tolerance or manufacturing release
K01_Front_1_stud | hardware | 4.999 | 60 | 4.999 | Mesh bounding box; no tolerance or manufacturing release
K01_Front_1_outer_washer | hardware | 15 | 1.2 | 14.995 | Mesh bounding box; no tolerance or manufacturing release
K01_Front_1_inner_washer | hardware | 15 | 1.2 | 14.995 | Mesh bounding box; no tolerance or manufacturing release
K01_Front_1_outer_nut | hardware | 9.238 | 5 | 8 | Mesh bounding box; no tolerance or manufacturing release
K01_Front_1_inner_nut | hardware | 9.238 | 5 | 8 | Mesh bounding box; no tolerance or manufacturing release
K01_Front_2_stud | hardware | 4.999 | 60 | 4.999 | Mesh bounding box; no tolerance or manufacturing release
K01_Front_2_outer_washer | hardware | 15 | 1.2 | 14.995 | Mesh bounding box; no tolerance or manufacturing release
K01_Front_2_inner_washer | hardware | 15 | 1.2 | 14.995 | Mesh bounding box; no tolerance or manufacturing release
K01_Front_2_outer_nut | hardware | 9.238 | 5 | 8 | Mesh bounding box; no tolerance or manufacturing release
K01_Front_2_inner_nut | hardware | 9.238 | 5 | 8 | Mesh bounding box; no tolerance or manufacturing release
K01_Front_3_stud | hardware | 4.999 | 60 | 4.999 | Mesh bounding box; no tolerance or manufacturing release
K01_Front_3_outer_washer | hardware | 15 | 1.2 | 14.995 | Mesh bounding box; no tolerance or manufacturing release
K01_Front_3_inner_washer | hardware | 15 | 1.2 | 14.995 | Mesh bounding box; no tolerance or manufacturing release
K01_Front_3_outer_nut | hardware | 9.238 | 5 | 8 | Mesh bounding box; no tolerance or manufacturing release
K01_Front_3_inner_nut | hardware | 9.238 | 5 | 8 | Mesh bounding box; no tolerance or manufacturing release
K01_Front_4_stud | hardware | 4.999 | 60 | 4.999 | Mesh bounding box; no tolerance or manufacturing release
K01_Front_4_outer_washer | hardware | 15 | 1.2 | 14.995 | Mesh bounding box; no tolerance or manufacturing release
K01_Front_4_inner_washer | hardware | 15 | 1.2 | 14.995 | Mesh bounding box; no tolerance or manufacturing release
K01_Front_4_outer_nut | hardware | 9.238 | 5 | 8 | Mesh bounding box; no tolerance or manufacturing release
K01_Front_4_inner_nut | hardware | 9.238 | 5 | 8 | Mesh bounding box; no tolerance or manufacturing release
K01_Front_5_stud | hardware | 4.999 | 60 | 4.999 | Mesh bounding box; no tolerance or manufacturing release
K01_Front_5_outer_washer | hardware | 15 | 1.2 | 14.995 | Mesh bounding box; no tolerance or manufacturing release
K01_Front_5_inner_washer | hardware | 15 | 1.2 | 14.995 | Mesh bounding box; no tolerance or manufacturing release
K01_Front_5_outer_nut | hardware | 9.238 | 5 | 8 | Mesh bounding box; no tolerance or manufacturing release
K01_Front_5_inner_nut | hardware | 9.238 | 5 | 8 | Mesh bounding box; no tolerance or manufacturing release
K01_Front_6_stud | hardware | 4.999 | 40 | 4.999 | Mesh bounding box; no tolerance or manufacturing release
K01_Front_6_outer_washer | hardware | 15 | 1.2 | 14.995 | Mesh bounding box; no tolerance or manufacturing release
K01_Front_6_inner_washer | hardware | 15 | 1.2 | 14.995 | Mesh bounding box; no tolerance or manufacturing release
K01_Front_6_outer_nut | hardware | 9.238 | 5 | 8 | Mesh bounding box; no tolerance or manufacturing release
K01_Front_6_inner_nut | hardware | 9.238 | 5 | 8 | Mesh bounding box; no tolerance or manufacturing release
K01_Front_7_stud | hardware | 4.999 | 40 | 4.999 | Mesh bounding box; no tolerance or manufacturing release
K01_Front_7_outer_washer | hardware | 15 | 1.2 | 14.995 | Mesh bounding box; no tolerance or manufacturing release
K01_Front_7_inner_washer | hardware | 15 | 1.2 | 14.995 | Mesh bounding box; no tolerance or manufacturing release
K01_Front_7_outer_nut | hardware | 9.238 | 5 | 8 | Mesh bounding box; no tolerance or manufacturing release
K01_Front_7_inner_nut | hardware | 9.238 | 5 | 8 | Mesh bounding box; no tolerance or manufacturing release
K01_Rear_0_stud | hardware | 4.999 | 60 | 4.999 | Mesh bounding box; no tolerance or manufacturing release
K01_Rear_0_outer_washer | hardware | 15 | 1.2 | 14.995 | Mesh bounding box; no tolerance or manufacturing release
K01_Rear_0_inner_washer | hardware | 15 | 1.2 | 14.995 | Mesh bounding box; no tolerance or manufacturing release
K01_Rear_0_outer_nut | hardware | 9.238 | 5 | 8 | Mesh bounding box; no tolerance or manufacturing release
K01_Rear_0_inner_nut | hardware | 9.238 | 5 | 8 | Mesh bounding box; no tolerance or manufacturing release
K01_Rear_1_stud | hardware | 4.999 | 60 | 4.999 | Mesh bounding box; no tolerance or manufacturing release
K01_Rear_1_outer_washer | hardware | 15 | 1.2 | 14.995 | Mesh bounding box; no tolerance or manufacturing release
K01_Rear_1_inner_washer | hardware | 15 | 1.2 | 14.995 | Mesh bounding box; no tolerance or manufacturing release
K01_Rear_1_outer_nut | hardware | 9.238 | 5 | 8 | Mesh bounding box; no tolerance or manufacturing release
K01_Rear_1_inner_nut | hardware | 9.238 | 5 | 8 | Mesh bounding box; no tolerance or manufacturing release
K01_Rear_2_stud | hardware | 4.999 | 60 | 4.999 | Mesh bounding box; no tolerance or manufacturing release
K01_Rear_2_outer_washer | hardware | 15 | 1.2 | 14.995 | Mesh bounding box; no tolerance or manufacturing release
K01_Rear_2_inner_washer | hardware | 15 | 1.2 | 14.995 | Mesh bounding box; no tolerance or manufacturing release
K01_Rear_2_outer_nut | hardware | 9.238 | 5 | 8 | Mesh bounding box; no tolerance or manufacturing release
K01_Rear_2_inner_nut | hardware | 9.238 | 5 | 8 | Mesh bounding box; no tolerance or manufacturing release
K01_Rear_3_stud | hardware | 4.999 | 60 | 4.999 | Mesh bounding box; no tolerance or manufacturing release
K01_Rear_3_outer_washer | hardware | 15 | 1.2 | 14.995 | Mesh bounding box; no tolerance or manufacturing release
K01_Rear_3_inner_washer | hardware | 15 | 1.2 | 14.995 | Mesh bounding box; no tolerance or manufacturing release
K01_Rear_3_outer_nut | hardware | 9.238 | 5 | 8 | Mesh bounding box; no tolerance or manufacturing release
K01_Rear_3_inner_nut | hardware | 9.238 | 5 | 8 | Mesh bounding box; no tolerance or manufacturing release
K01_Rear_4_stud | hardware | 4.999 | 60 | 4.999 | Mesh bounding box; no tolerance or manufacturing release
K01_Rear_4_outer_washer | hardware | 15 | 1.2 | 14.995 | Mesh bounding box; no tolerance or manufacturing release
K01_Rear_4_inner_washer | hardware | 15 | 1.2 | 14.995 | Mesh bounding box; no tolerance or manufacturing release
K01_Rear_4_outer_nut | hardware | 9.238 | 5 | 8 | Mesh bounding box; no tolerance or manufacturing release
K01_Rear_4_inner_nut | hardware | 9.238 | 5 | 8 | Mesh bounding box; no tolerance or manufacturing release
K01_Rear_5_stud | hardware | 4.999 | 60 | 4.999 | Mesh bounding box; no tolerance or manufacturing release
K01_Rear_5_outer_washer | hardware | 15 | 1.2 | 14.995 | Mesh bounding box; no tolerance or manufacturing release
K01_Rear_5_inner_washer | hardware | 15 | 1.2 | 14.995 | Mesh bounding box; no tolerance or manufacturing release
K01_Rear_5_outer_nut | hardware | 9.238 | 5 | 8 | Mesh bounding box; no tolerance or manufacturing release
K01_Rear_5_inner_nut | hardware | 9.238 | 5 | 8 | Mesh bounding box; no tolerance or manufacturing release
K01_Rear_6_stud | hardware | 4.999 | 40 | 4.999 | Mesh bounding box; no tolerance or manufacturing release
K01_Rear_6_outer_washer | hardware | 15 | 1.2 | 14.995 | Mesh bounding box; no tolerance or manufacturing release
K01_Rear_6_inner_washer | hardware | 15 | 1.2 | 14.995 | Mesh bounding box; no tolerance or manufacturing release
K01_Rear_6_outer_nut | hardware | 9.238 | 5 | 8 | Mesh bounding box; no tolerance or manufacturing release
K01_Rear_6_inner_nut | hardware | 9.238 | 5 | 8 | Mesh bounding box; no tolerance or manufacturing release
K01_Rear_7_stud | hardware | 4.999 | 40 | 4.999 | Mesh bounding box; no tolerance or manufacturing release
K01_Rear_7_outer_washer | hardware | 15 | 1.2 | 14.995 | Mesh bounding box; no tolerance or manufacturing release
K01_Rear_7_inner_washer | hardware | 15 | 1.2 | 14.995 | Mesh bounding box; no tolerance or manufacturing release
K01_Rear_7_outer_nut | hardware | 9.238 | 5 | 8 | Mesh bounding box; no tolerance or manufacturing release
K01_Rear_7_inner_nut | hardware | 9.238 | 5 | 8 | Mesh bounding box; no tolerance or manufacturing release
K03_Outer_stop_False_0 | hardware | 10 | 3 | 9.997 | Mesh bounding box; no tolerance or manufacturing release
K03_Outer_stop_False_1 | hardware | 10 | 3 | 9.997 | Mesh bounding box; no tolerance or manufacturing release
K03_Outer_stop_False_2 | hardware | 10 | 3 | 9.997 | Mesh bounding box; no tolerance or manufacturing release
K03_Outer_stop_False_3 | hardware | 10 | 3 | 9.997 | Mesh bounding box; no tolerance or manufacturing release
K03_Outer_stop_False_4 | hardware | 10 | 3 | 9.997 | Mesh bounding box; no tolerance or manufacturing release
K03_Outer_stop_False_5 | hardware | 10 | 3 | 9.997 | Mesh bounding box; no tolerance or manufacturing release
K03_Outer_stop_False_6 | hardware | 10 | 3 | 9.997 | Mesh bounding box; no tolerance or manufacturing release
K03_Outer_stop_False_7 | hardware | 10 | 3 | 9.997 | Mesh bounding box; no tolerance or manufacturing release
K04_Inner_stop_False_0 | hardware | 6.5 | 36 | 6.498 | Mesh bounding box; no tolerance or manufacturing release
K04_Inner_stop_False_1 | hardware | 6.5 | 36 | 6.498 | Mesh bounding box; no tolerance or manufacturing release
K04_Inner_stop_False_2 | hardware | 6.5 | 36 | 6.498 | Mesh bounding box; no tolerance or manufacturing release
K04_Inner_stop_False_3 | hardware | 6.5 | 36 | 6.498 | Mesh bounding box; no tolerance or manufacturing release
K03_Outer_stop_True_0 | hardware | 10 | 3 | 9.997 | Mesh bounding box; no tolerance or manufacturing release
K03_Outer_stop_True_1 | hardware | 10 | 3 | 9.997 | Mesh bounding box; no tolerance or manufacturing release
K03_Outer_stop_True_2 | hardware | 10 | 3 | 9.997 | Mesh bounding box; no tolerance or manufacturing release
K03_Outer_stop_True_3 | hardware | 10 | 3 | 9.997 | Mesh bounding box; no tolerance or manufacturing release
K03_Outer_stop_True_4 | hardware | 10 | 3 | 9.997 | Mesh bounding box; no tolerance or manufacturing release
K03_Outer_stop_True_5 | hardware | 10 | 3 | 9.997 | Mesh bounding box; no tolerance or manufacturing release
K03_Outer_stop_True_6 | hardware | 10 | 3 | 9.997 | Mesh bounding box; no tolerance or manufacturing release
K03_Outer_stop_True_7 | hardware | 10 | 3 | 9.997 | Mesh bounding box; no tolerance or manufacturing release
K04_Inner_stop_True_0 | hardware | 6.5 | 36 | 6.498 | Mesh bounding box; no tolerance or manufacturing release
K04_Inner_stop_True_1 | hardware | 6.5 | 36 | 6.498 | Mesh bounding box; no tolerance or manufacturing release
K04_Inner_stop_True_2 | hardware | 6.5 | 36 | 6.498 | Mesh bounding box; no tolerance or manufacturing release
K04_Inner_stop_True_3 | hardware | 6.5 | 36 | 6.498 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_1_1_screw | hardware | 7 | 6.998 | 54 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_1_1_top_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_1_1_bottom_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_1_1_nut | hardware | 8.083 | 7 | 5 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_1_2_screw | hardware | 7 | 6.998 | 54 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_1_2_top_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_1_2_bottom_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_1_2_nut | hardware | 8.083 | 7 | 5 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_1_3_screw | hardware | 7 | 6.998 | 54 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_1_3_top_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_1_3_bottom_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_1_3_nut | hardware | 8.083 | 7 | 5 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_1_4_screw | hardware | 7 | 6.998 | 54 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_1_4_top_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_1_4_bottom_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_1_4_nut | hardware | 8.083 | 7 | 5 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_2_1_screw | hardware | 7 | 6.998 | 54 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_2_1_top_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_2_1_bottom_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_2_1_nut | hardware | 8.083 | 7 | 5 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_2_2_screw | hardware | 7 | 6.998 | 54 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_2_2_top_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_2_2_bottom_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_2_2_nut | hardware | 8.083 | 7 | 5 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_2_3_screw | hardware | 7 | 6.998 | 54 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_2_3_top_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_2_3_bottom_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_2_3_nut | hardware | 8.083 | 7 | 5 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_2_4_screw | hardware | 7 | 6.998 | 54 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_2_4_top_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_2_4_bottom_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_2_4_nut | hardware | 8.083 | 7 | 5 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_3_1_screw | hardware | 7 | 6.998 | 54 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_3_1_top_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_3_1_bottom_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_3_1_nut | hardware | 8.083 | 7 | 5 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_3_2_screw | hardware | 7 | 6.998 | 54 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_3_2_top_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_3_2_bottom_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_3_2_nut | hardware | 8.083 | 7 | 5 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_3_3_screw | hardware | 7 | 6.998 | 54 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_3_3_top_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_3_3_bottom_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_3_3_nut | hardware | 8.083 | 7 | 5 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_3_4_screw | hardware | 7 | 6.998 | 54 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_3_4_top_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_3_4_bottom_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_3_4_nut | hardware | 8.083 | 7 | 5 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_4_1_screw | hardware | 7 | 6.998 | 54 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_4_1_top_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_4_1_bottom_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_4_1_nut | hardware | 8.083 | 7 | 5 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_4_2_screw | hardware | 7 | 6.998 | 54 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_4_2_top_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_4_2_bottom_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_4_2_nut | hardware | 8.083 | 7 | 5 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_4_3_screw | hardware | 7 | 6.998 | 54 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_4_3_top_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_4_3_bottom_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_4_3_nut | hardware | 8.083 | 7 | 5 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_4_4_screw | hardware | 7 | 6.998 | 54 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_4_4_top_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_4_4_bottom_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
K02_Fan_bolt_4_4_nut | hardware | 8.083 | 7 | 5 | Mesh bounding box; no tolerance or manufacturing release
K06_End_False_19_105_screw | hardware | 44 | 6.998 | 7 | Mesh bounding box; no tolerance or manufacturing release
K06_End_False_19_105_outer_washer | hardware | 1 | 11.996 | 12 | Mesh bounding box; no tolerance or manufacturing release
K06_End_False_19_105_inner_washer | hardware | 1 | 11.996 | 12 | Mesh bounding box; no tolerance or manufacturing release
K06_End_False_19_105_nut | hardware | 5 | 7 | 8.083 | Mesh bounding box; no tolerance or manufacturing release
K06_End_False_19_205_screw | hardware | 44 | 6.998 | 7 | Mesh bounding box; no tolerance or manufacturing release
K06_End_False_19_205_outer_washer | hardware | 1 | 11.996 | 12 | Mesh bounding box; no tolerance or manufacturing release
K06_End_False_19_205_inner_washer | hardware | 1 | 11.996 | 12 | Mesh bounding box; no tolerance or manufacturing release
K06_End_False_19_205_nut | hardware | 5 | 7 | 8.083 | Mesh bounding box; no tolerance or manufacturing release
K06_End_False_19_405_screw | hardware | 44 | 6.998 | 7 | Mesh bounding box; no tolerance or manufacturing release
K06_End_False_19_405_outer_washer | hardware | 1 | 11.996 | 12 | Mesh bounding box; no tolerance or manufacturing release
K06_End_False_19_405_inner_washer | hardware | 1 | 11.996 | 12 | Mesh bounding box; no tolerance or manufacturing release
K06_End_False_19_405_nut | hardware | 5 | 7 | 8.083 | Mesh bounding box; no tolerance or manufacturing release
K06_End_False_19_505_screw | hardware | 44 | 6.998 | 7 | Mesh bounding box; no tolerance or manufacturing release
K06_End_False_19_505_outer_washer | hardware | 1 | 11.996 | 12 | Mesh bounding box; no tolerance or manufacturing release
K06_End_False_19_505_inner_washer | hardware | 1 | 11.996 | 12 | Mesh bounding box; no tolerance or manufacturing release
K06_End_False_19_505_nut | hardware | 5 | 7 | 8.083 | Mesh bounding box; no tolerance or manufacturing release
K06_End_False_341_105_screw | hardware | 44 | 6.998 | 7 | Mesh bounding box; no tolerance or manufacturing release
K06_End_False_341_105_outer_washer | hardware | 1 | 11.996 | 12 | Mesh bounding box; no tolerance or manufacturing release
K06_End_False_341_105_inner_washer | hardware | 1 | 11.996 | 12 | Mesh bounding box; no tolerance or manufacturing release
K06_End_False_341_105_nut | hardware | 5 | 7 | 8.083 | Mesh bounding box; no tolerance or manufacturing release
K06_End_False_341_205_screw | hardware | 44 | 6.998 | 7 | Mesh bounding box; no tolerance or manufacturing release
K06_End_False_341_205_outer_washer | hardware | 1 | 11.996 | 12 | Mesh bounding box; no tolerance or manufacturing release
K06_End_False_341_205_inner_washer | hardware | 1 | 11.996 | 12 | Mesh bounding box; no tolerance or manufacturing release
K06_End_False_341_205_nut | hardware | 5 | 7 | 8.083 | Mesh bounding box; no tolerance or manufacturing release
K06_End_False_341_405_screw | hardware | 44 | 6.998 | 7 | Mesh bounding box; no tolerance or manufacturing release
K06_End_False_341_405_outer_washer | hardware | 1 | 11.996 | 12 | Mesh bounding box; no tolerance or manufacturing release
K06_End_False_341_405_inner_washer | hardware | 1 | 11.996 | 12 | Mesh bounding box; no tolerance or manufacturing release
K06_End_False_341_405_nut | hardware | 5 | 7 | 8.083 | Mesh bounding box; no tolerance or manufacturing release
K06_End_False_341_505_screw | hardware | 44 | 6.998 | 7 | Mesh bounding box; no tolerance or manufacturing release
K06_End_False_341_505_outer_washer | hardware | 1 | 11.996 | 12 | Mesh bounding box; no tolerance or manufacturing release
K06_End_False_341_505_inner_washer | hardware | 1 | 11.996 | 12 | Mesh bounding box; no tolerance or manufacturing release
K06_End_False_341_505_nut | hardware | 5 | 7 | 8.083 | Mesh bounding box; no tolerance or manufacturing release
K06_End_True_19_105_screw | hardware | 44 | 6.998 | 7 | Mesh bounding box; no tolerance or manufacturing release
K06_End_True_19_105_outer_washer | hardware | 1 | 11.996 | 12 | Mesh bounding box; no tolerance or manufacturing release
K06_End_True_19_105_inner_washer | hardware | 1 | 11.996 | 12 | Mesh bounding box; no tolerance or manufacturing release
K06_End_True_19_105_nut | hardware | 5 | 7 | 8.083 | Mesh bounding box; no tolerance or manufacturing release
K06_End_True_19_205_screw | hardware | 44 | 6.998 | 7 | Mesh bounding box; no tolerance or manufacturing release
K06_End_True_19_205_outer_washer | hardware | 1 | 11.996 | 12 | Mesh bounding box; no tolerance or manufacturing release
K06_End_True_19_205_inner_washer | hardware | 1 | 11.996 | 12 | Mesh bounding box; no tolerance or manufacturing release
K06_End_True_19_205_nut | hardware | 5 | 7 | 8.083 | Mesh bounding box; no tolerance or manufacturing release
K06_End_True_19_405_screw | hardware | 44 | 6.998 | 7 | Mesh bounding box; no tolerance or manufacturing release
K06_End_True_19_405_outer_washer | hardware | 1 | 11.996 | 12 | Mesh bounding box; no tolerance or manufacturing release
K06_End_True_19_405_inner_washer | hardware | 1 | 11.996 | 12 | Mesh bounding box; no tolerance or manufacturing release
K06_End_True_19_405_nut | hardware | 5 | 7 | 8.083 | Mesh bounding box; no tolerance or manufacturing release
K06_End_True_19_505_screw | hardware | 44 | 6.998 | 7 | Mesh bounding box; no tolerance or manufacturing release
K06_End_True_19_505_outer_washer | hardware | 1 | 11.996 | 12 | Mesh bounding box; no tolerance or manufacturing release
K06_End_True_19_505_inner_washer | hardware | 1 | 11.996 | 12 | Mesh bounding box; no tolerance or manufacturing release
K06_End_True_19_505_nut | hardware | 5 | 7 | 8.083 | Mesh bounding box; no tolerance or manufacturing release
K06_End_True_341_105_screw | hardware | 44 | 6.998 | 7 | Mesh bounding box; no tolerance or manufacturing release
K06_End_True_341_105_outer_washer | hardware | 1 | 11.996 | 12 | Mesh bounding box; no tolerance or manufacturing release
K06_End_True_341_105_inner_washer | hardware | 1 | 11.996 | 12 | Mesh bounding box; no tolerance or manufacturing release
K06_End_True_341_105_nut | hardware | 5 | 7 | 8.083 | Mesh bounding box; no tolerance or manufacturing release
K06_End_True_341_205_screw | hardware | 44 | 6.998 | 7 | Mesh bounding box; no tolerance or manufacturing release
K06_End_True_341_205_outer_washer | hardware | 1 | 11.996 | 12 | Mesh bounding box; no tolerance or manufacturing release
K06_End_True_341_205_inner_washer | hardware | 1 | 11.996 | 12 | Mesh bounding box; no tolerance or manufacturing release
K06_End_True_341_205_nut | hardware | 5 | 7 | 8.083 | Mesh bounding box; no tolerance or manufacturing release
K06_End_True_341_405_screw | hardware | 44 | 6.998 | 7 | Mesh bounding box; no tolerance or manufacturing release
K06_End_True_341_405_outer_washer | hardware | 1 | 11.996 | 12 | Mesh bounding box; no tolerance or manufacturing release
K06_End_True_341_405_inner_washer | hardware | 1 | 11.996 | 12 | Mesh bounding box; no tolerance or manufacturing release
K06_End_True_341_405_nut | hardware | 5 | 7 | 8.083 | Mesh bounding box; no tolerance or manufacturing release
K06_End_True_341_505_screw | hardware | 44 | 6.998 | 7 | Mesh bounding box; no tolerance or manufacturing release
K06_End_True_341_505_outer_washer | hardware | 1 | 11.996 | 12 | Mesh bounding box; no tolerance or manufacturing release
K06_End_True_341_505_inner_washer | hardware | 1 | 11.996 | 12 | Mesh bounding box; no tolerance or manufacturing release
K06_End_True_341_505_nut | hardware | 5 | 7 | 8.083 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_False_20_155_screw | hardware | 7 | 44 | 6.998 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_False_20_155_outer_washer | hardware | 12 | 1 | 11.996 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_False_20_155_inner_washer | hardware | 12 | 1 | 11.996 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_False_20_155_nut | hardware | 8.083 | 5 | 7 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_False_20_255_screw | hardware | 7 | 44 | 6.998 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_False_20_255_outer_washer | hardware | 12 | 1 | 11.996 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_False_20_255_inner_washer | hardware | 12 | 1 | 11.996 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_False_20_255_nut | hardware | 8.083 | 5 | 7 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_False_20_355_screw | hardware | 7 | 44 | 6.998 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_False_20_355_outer_washer | hardware | 12 | 1 | 11.996 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_False_20_355_inner_washer | hardware | 12 | 1 | 11.996 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_False_20_355_nut | hardware | 8.083 | 5 | 7 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_False_20_455_screw | hardware | 7 | 44 | 6.998 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_False_20_455_outer_washer | hardware | 12 | 1 | 11.996 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_False_20_455_inner_washer | hardware | 12 | 1 | 11.996 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_False_20_455_nut | hardware | 8.083 | 5 | 7 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_False_530_155_screw | hardware | 7 | 44 | 6.998 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_False_530_155_outer_washer | hardware | 12 | 1 | 11.996 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_False_530_155_inner_washer | hardware | 12 | 1 | 11.996 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_False_530_155_nut | hardware | 8.083 | 5 | 7 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_False_530_255_screw | hardware | 7 | 44 | 6.998 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_False_530_255_outer_washer | hardware | 12 | 1 | 11.996 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_False_530_255_inner_washer | hardware | 12 | 1 | 11.996 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_False_530_255_nut | hardware | 8.083 | 5 | 7 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_False_530_355_screw | hardware | 7 | 44 | 6.998 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_False_530_355_outer_washer | hardware | 12 | 1 | 11.996 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_False_530_355_inner_washer | hardware | 12 | 1 | 11.996 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_False_530_355_nut | hardware | 8.083 | 5 | 7 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_False_530_455_screw | hardware | 7 | 44 | 6.998 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_False_530_455_outer_washer | hardware | 12 | 1 | 11.996 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_False_530_455_inner_washer | hardware | 12 | 1 | 11.996 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_False_530_455_nut | hardware | 8.083 | 5 | 7 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_True_20_155_screw | hardware | 7 | 44 | 6.998 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_True_20_155_outer_washer | hardware | 12 | 1 | 11.996 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_True_20_155_inner_washer | hardware | 12 | 1 | 11.996 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_True_20_155_nut | hardware | 8.083 | 5 | 7 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_True_20_255_screw | hardware | 7 | 44 | 6.998 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_True_20_255_outer_washer | hardware | 12 | 1 | 11.996 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_True_20_255_inner_washer | hardware | 12 | 1 | 11.996 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_True_20_255_nut | hardware | 8.083 | 5 | 7 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_True_20_355_screw | hardware | 7 | 44 | 6.998 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_True_20_355_outer_washer | hardware | 12 | 1 | 11.996 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_True_20_355_inner_washer | hardware | 12 | 1 | 11.996 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_True_20_355_nut | hardware | 8.083 | 5 | 7 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_True_20_455_screw | hardware | 7 | 44 | 6.998 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_True_20_455_outer_washer | hardware | 12 | 1 | 11.996 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_True_20_455_inner_washer | hardware | 12 | 1 | 11.996 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_True_20_455_nut | hardware | 8.083 | 5 | 7 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_True_530_155_screw | hardware | 7 | 44 | 6.998 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_True_530_155_outer_washer | hardware | 12 | 1 | 11.996 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_True_530_155_inner_washer | hardware | 12 | 1 | 11.996 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_True_530_155_nut | hardware | 8.083 | 5 | 7 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_True_530_255_screw | hardware | 7 | 44 | 6.998 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_True_530_255_outer_washer | hardware | 12 | 1 | 11.996 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_True_530_255_inner_washer | hardware | 12 | 1 | 11.996 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_True_530_255_nut | hardware | 8.083 | 5 | 7 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_True_530_355_screw | hardware | 7 | 44 | 6.998 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_True_530_355_outer_washer | hardware | 12 | 1 | 11.996 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_True_530_355_inner_washer | hardware | 12 | 1 | 11.996 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_True_530_355_nut | hardware | 8.083 | 5 | 7 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_True_530_455_screw | hardware | 7 | 44 | 6.998 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_True_530_455_outer_washer | hardware | 12 | 1 | 11.996 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_True_530_455_inner_washer | hardware | 12 | 1 | 11.996 | Mesh bounding box; no tolerance or manufacturing release
K07_Seat_True_530_455_nut | hardware | 8.083 | 5 | 7 | Mesh bounding box; no tolerance or manufacturing release
K10_washer_H10_False_19_19 | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
K10_head_H10_False_19_19 | hardware | 7 | 6.998 | 4 | Mesh bounding box; no tolerance or manufacturing release
K10_washer_H10_False_19_341 | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
K10_head_H10_False_19_341 | hardware | 7 | 6.998 | 4 | Mesh bounding box; no tolerance or manufacturing release
K10_washer_H10_False_531_19 | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
K10_head_H10_False_531_19 | hardware | 7 | 6.998 | 4 | Mesh bounding box; no tolerance or manufacturing release
K10_washer_H10_False_531_341 | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
K10_head_H10_False_531_341 | hardware | 7 | 6.998 | 4 | Mesh bounding box; no tolerance or manufacturing release
K10_washer_H10_True_19_19 | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
K10_head_H10_True_19_19 | hardware | 7 | 6.998 | 4 | Mesh bounding box; no tolerance or manufacturing release
K10_washer_H10_True_19_341 | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
K10_head_H10_True_19_341 | hardware | 7 | 6.998 | 4 | Mesh bounding box; no tolerance or manufacturing release
K10_washer_H10_True_531_19 | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
K10_head_H10_True_531_19 | hardware | 7 | 6.998 | 4 | Mesh bounding box; no tolerance or manufacturing release
K10_washer_H10_True_531_341 | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
K10_head_H10_True_531_341 | hardware | 7 | 6.998 | 4 | Mesh bounding box; no tolerance or manufacturing release
K08_M08_Foot_25_15_screw | hardware | 7 | 6.998 | 34 | Mesh bounding box; no tolerance or manufacturing release
K08_M08_Foot_25_15_lower_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
K08_M08_Foot_25_15_upper_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
K08_M08_Foot_25_15_nut | hardware | 8.083 | 7 | 5 | Mesh bounding box; no tolerance or manufacturing release
K08_M08_Foot_25_315_screw | hardware | 7 | 6.998 | 34 | Mesh bounding box; no tolerance or manufacturing release
K08_M08_Foot_25_315_lower_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
K08_M08_Foot_25_315_upper_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
K08_M08_Foot_25_315_nut | hardware | 8.083 | 7 | 5 | Mesh bounding box; no tolerance or manufacturing release
K08_M08_Foot_495_15_screw | hardware | 7 | 6.998 | 34 | Mesh bounding box; no tolerance or manufacturing release
K08_M08_Foot_495_15_lower_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
K08_M08_Foot_495_15_upper_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
K08_M08_Foot_495_15_nut | hardware | 8.083 | 7 | 5 | Mesh bounding box; no tolerance or manufacturing release
K08_M08_Foot_495_315_screw | hardware | 7 | 6.998 | 34 | Mesh bounding box; no tolerance or manufacturing release
K08_M08_Foot_495_315_lower_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
K08_M08_Foot_495_315_upper_washer | hardware | 12 | 11.996 | 1 | Mesh bounding box; no tolerance or manufacturing release
K08_M08_Foot_495_315_nut | hardware | 8.083 | 7 | 5 | Mesh bounding box; no tolerance or manufacturing release